## Bug and issue Test
# | Type | Description | Feedback TC | Comment | Status
1 | Issue |  | We will keep link there in list view of customers. on clicking of that it will redirect to product list page of that specific customer and can view details of each product but can not edit it. | 15.03.2021 - AL That could work | Approved by client
2 | Issue | In the product master we need to be able to choose product category and subcategory | We can have only sub-category selection list that might suffice the purpose. As if we keep both then first need to select category and from selected category subcategory will fill up and then again need to select it. So we can avoid it by placing subcategory selection only. | 15.03.2021 - AL I here meant, when creating a product in the product master, they need to be able to choose Category and Subcategory for the product they create. | Pending | Done
3 | Issue | In the product master, relations are not to category/Subcategory but to products, (ex BOM (Bill of material) which products are part of a product assembly) | Yes, We will update it with product multi selection. all products of that customer will be displayed if it is assigned to that customer or added by itself only. | 15.03.21 - AL Need to see/understand how you will solve this | Pending | Done
4 | Issue | When creating users the location field needs to come from the location master. | Can you please explain this? as we understood that location is as per customer. | 15.03.2021 - AL When creating a user for a customer with multiple locations. The location field cannot be a textfield, but possible to choose from the location master. | Pending | Done
5 | Bug/Error | Upload document does not work for product document | We will check this |  | Pending | Done
6 | Issue | Product checklist, not able to create any checklist? | In check list we just need to provide Question only for specific product as it is now and on client portal side it will display as checkbox with entered Question so user just need to select it if it is done ? Please let us know if we understood differently. | 15.03.2021 This module could be removed/Renamed and replaced by maintenance checklist. Lets discuss this |  | Done, Change name of product Checklist to maintenance checklist.
7 | ReqForChange | Can we have in addition to the logo "Service Management Admin" as heading on the site? | Can you please explain this? Exactly where it needs to keep ? | To the right of the logo | Pending | Service Management Admin beside logo
8 | ReqForChange | Can we have a view option, not only edit and delete in the lists? | Yes, we will work on that |  | Pending | Doen
9 | Bug/Error | . When adding a location - Product FAQ added shows up in the upper right corner | Yes, we will fix this. |  | Pending | Pending
10 | Issue | Document Category needs to show in the Product Document Details list | Yes, we will add this. |  | Pending | Show cloumn name doc cat name in docList
11 | Bug/Error | When creating a product subcategory name, "Manage personal information appears" in the data field | Can you please explain this as we do not able to understand this? | I need to show you | Pending
12 | Bug/Error | In product master, data i added are removed after i have created new Attribute key and value, ex weight in product winch | It is working fine can you please re-check it ? | It seems to work now. | Resolved
13 | Bug/Error | Cancel doesn't work in the lists | Can you please explain this as we do not able to understand this? | 15.03.2021 Ex. When in a productform, when i press the cancel button at the bottom of the page, i expect to get back out to the product list. Pressing the cancel button now, and nothing happens. Lets review this | Pending | Cnacel redirect to the detail page to all pages
14 | ReqForChange | Colour code in company form does not need to be mandatory. Can we have a default colour and they can change colour if they like? | Yes, we will update it |  | Pending
15 | Bug/Error | Not able to upload video | Yes, we will fix it. |  | Pending
16 |  | When adding video, the Product checklist shows in the menu heading | Yes, we will fix it. |  | Pending
17 | ReqForChange | Can we rename Company to Customer? | Yes, We will change it |  | Pending
18 | Issue | No user will be the admin user of customer portal |  | 15.03.2021 I expect it is the Admin user that will be the administrator of the customer portal | Approved by client
19 |  | Check Company Name and User Name for unique data to be saved no dublicate entry in company and user should be added

## Requirement
One level Integration | Requirement | Comments
| - QRON is default customer and can add multiple customers. | QRON is the QRON solution provider, and can add multiple customers to the solution
| - QRON can add two types of users only (QRON Admin , customer Admin (for Techly,Tech1 etc..) | Correct
| - QRON can add location for customer or Users ? | QRON need only to register customers with mainoffice/billing information, and Customer admin user
| - QRON can add products which are under category and subcategory. | QRON will add only QRON solution as product.
| - QRON can manage documents which are linked to products only (entered by QRON only). | Correct
| - QRON can manage videos which are linked to products only (entered by QRON only). | Correct
| - QRON can assigned products to customers (like Techly, Tech1 etc..) | QRON will add QRON as product and distribute login to customers.
| - When any products assigned to any customer then all documents and videos are assigned to that customer automatically. | Need you to clarify… Videos, documents, checklists, FAQ's etc. are assigned to products and products are assigned to customers
Second level Integration (QRON has added one customer named as "Techly") | Techly is a example customer of a customer of QRON
| - Techly can add multiple customers (like XYZ, ABC etc..) | Correct
| - Techly can add three types of user only (Techly Admin , customer Admin (for XYZ,ABC etc..), customer service contractor (for XYZ,ABC etc..) | Correct
| - Techly can add location for customer or Users ? | Correct
| - Techly can see all the category/subcategory/products/documents/videos which are assigned by parent customer (QRON) | Correct, but i think we need to discuss the role of QRON to be totally clear…
| - Techly cannot edit category/subcategory/products/documents/videos which are assigned by parent customer (QRON). | Correct
| - Techly can add its own category/subcategory/products/documents/videos. This will not be displayed to parent customer(QRON). | Correct
| - Techly can manage documents which are linked to products(entered by Techly only). | Correct
| - Techly can manage videos which are linked to products (entered by Techly only). | Correct
| - Techly can assigned products to customers (like XYZ, ABC etc..) | Correct
| - Techly can assigned parent products to its customer too (like XYZ, ABC etc..) | Correct
| - When any products assigned to any customer then all documents and videos are assigned to that customer automatically. | Correct, Videos, documents, checklists, FAQ's etc. are assigned to products and products are assigned to customers
Third level Integration (Techly has added one customer named as "XYZ")
| - XYZ can add two types of users (XYZ admin , XYZ service contractor) | No, Techly as Service Provider creates users that can access the Client Service portal.
| QRON customer portal will be accessible by its child customers (like Techly and its child customer XYZ) | Probably correct if i understand you correctly, but need to clarify.

## Ark2
Type | Status
Issue | Open
Bug/Error | Approved by client
ReqForChange | Work in progress
Pending
Resolved
Closed